## Slide 1
Park Rapids Additions and Renovations
PARK RAPIDS PUBLIC SCHOOLS
Board Update
High School – BP #1 Precast – Approval to Award Contract
October 3rd, 2022

## Slide 2
What’s Been Done?
Park Rapids Additions and Renovations
Approx. 65% Complete with Construction Documents at High School
  Received Bids for BP#1, Precast
Tennis Court Punchlist Completion / Closeout
Metal Panel Refinish Project
  Nearing completion
Progress on the Bus Garage Design
  Nearing a DD level design
  Have held User Group meetings

## Slide 3
What’s Been Done? (continued)
Park Rapids Additions and Renovations
Weekly Design Coordination Meetings
  Coordination meetings with all design disciplines
Discussed Exterior Finishes
  Metal Panels, Precast, Brick, Windows
Furniture Meetings
  Held User Group meetings to discuss needs

## Slide 4
Upcoming
Park Rapids Additions and Renovations
Continue with Construction Documents at Secondary
  CD Completion (Design), December 5th
Construction Documents at Century Parent Pick-up / Drop-off
Design Development Documents at Century Renovations
Bus Garage Design
  DD’s Complete, End of October
Playground Design
  User Group Meeting recently held
Furniture User Group Meetings

## Slide 5
Preliminary Overall Schedule – Subject to Change
Park Rapids Additions and Renovations
Tennis Courts – Summer of ‘22
Bus Garage – Commencing Summer of ‘23
Elementary Parent Pick-up / Drop-off – Summer of ‘23
Elementary Renovations – Summer of ‘24
Frank White Demolition – May/June of ‘23
Secondary Additions – Commence Summer of ‘23 – Complete August of ’24
Secondary Additions (ALC/Trans./Kitchen) – Commence Summer of ‘24 and – Complete
May of ’25 (Reference Phasing Plan)
Secondary Phase 1 Renovations – Summer of ’24 (Reference Phasing Plan)
Secondary Phase 2 Renovations – Summer of ’25 (Reference Phasing Plan)

## Slide 6
HS, Bid Package #1 – Precast, Recommendation to Award
Park Rapids Additions and Renovations
Received (3) Bids – Good Coverage!
Low Contractor, Wells Concrete
Wells Bid Came In Under the Estimate

## Slide 9
HS, Bid Package #1 – Precast, Recommendation to Award
Park Rapids Additions and Renovations
We recommend awarding the contract to Wells Concrete

## Slide 10
Questions?