## Slide 1
Park Rapids Additions and Renovations
PARK RAPIDS PUBLIC SCHOOLS
Board Update and Bus Garage D.D. Presentation
November 22nd, 2022

## Slide 2
What’s Been Done?
Park Rapids Additions and Renovations
Approx. 90% Complete with Construction Documents at High School
  Received Bids and Awarded BP#1, Precast, to Wells Concrete
Approx. 70% Complete with Construction Documents at Century Civil Project
Progress on the Bus Garage Design
  100% Complete with Design Development Drawings
Approx. 70% with Design Development Documents at the Century Renovations
Metal Panel Refinish Project
  Punchlist Completed

## Slide 3
What’s Been Done? (continued)
Park Rapids Additions and Renovations
Weekly Design Coordination Meetings
  Coordination meetings with all design disciplines
Furniture Meetings
  Held additional meetings

## Slide 4
Upcoming
Park Rapids Additions and Renovations
Continue with Construction Documents at Secondary
  CD Completion (Design), December 5th
Continue Construction Documents at the Century Parent Pick-up / Drop-off
Continue Design Development Documents at Century Renovations
Bus Garage
  Move into the CD Phase

## Slide 5
Upcoming (cont.)
Park Rapids Additions and Renovations
Current Bid Opening Schedule
  1/24/23 High School Additions and Improvements
  2/7/23 Bus Garage
  2/14/23 Century Parent Pick-up Drop-off
  12/13/23 Century Renovations

## Slide 6
Preliminary Overall Schedule – Subject to Change
Park Rapids Additions and Renovations
Tennis Courts – Summer of ‘22
Bus Garage – Summer of ‘23
Elementary Parent Pick-up / Drop-off – Summer of ‘23
Elementary Renovations – Summer of ‘24
Frank White Demolition – May/June of ‘23
Secondary Additions – Commence Summer of ‘23 – Complete August of ’24
Secondary Additions (ALC/Trans./Kitchen) – Commence Summer of ‘24 and – Complete
May of ’25 (Reference Phasing Plan)
Secondary Phase 1 Renovations – Summer of ’24 (Reference Phasing Plan)
Secondary Phase 2 Renovations – Summer of ’25 (Reference Phasing Plan)

## Slide 7
Bus Garage Design Development
Park Rapids Additions and Renovations
We’ll Review the Following:
  Plan Review
  Schedule
  Construction Estimate

## Slide 8
Site Plan

## Slide 9
Utility Plan

## Slide 10
Bus Storage – Floor Plan

## Slide 11
Maintenance Building – Floor Plan

## Slide 12
Bus Storage – East (Main) Elevation

## Slide 13
Bus Storage – West Elevation

## Slide 14
Maintenance Building – East (Main) Elevation

## Slide 15
Bus Garage Design Development - Schedule

## Slide 16
Bus Garage Design Development - Estimate
Park Rapids Additions and Renovations

## Slide 17
Bus Garage Design Development
Park Rapids Additions and Renovations
We Recommend to Approve the Bus Garage Design Development as Presented
with the Authorization to Proceed with Construction Documents

## Slide 18
Questions?