## Slide 1
Park Rapids Additions and Renovations
PARK RAPIDS PUBLIC SCHOOLS
Project 309 Board Update
December 5th , 2022

## Slide 2
What’s Been Done?
Park Rapids Additions and Renovations
100% Completed with Construction Documents at High School
  ICS is working on Front-End Specs and CD Estimate
Approx. 75% Complete with Construction Documents at Century Civil Project
Progress on the Bus Garage Design
  Design Team is working on the Construction Documents
Approx. 75% with Design Development Documents at the Century Renovations
Weekly Design Coordination Meetings
  Coordination meetings with all design disciplines

## Slide 3
Upcoming
Park Rapids Additions and Renovations
Continue working through the Front-End Specs for the Secondary
Continue Construction Documents at the Century Parent Pick-up / Drop-off
Continue Design Development Documents at Century Renovations
Continue Construction Documents at the Bus Garage

## Slide 4
Upcoming (cont.)
Park Rapids Additions and Renovations
Current Bid Opening Schedule
  1/24/23 High School Additions and Improvements
  2/7/23 Bus Garage
  2/14/23 Century Parent Pick-up Drop-off
  12/13/23 Century Renovations

## Slide 5
Preliminary Overall Schedule – Subject to Change
Park Rapids Additions and Renovations
Tennis Courts – Summer of ‘22
Bus Garage – Summer of ‘23
Elementary Parent Pick-up / Drop-off – Summer of ‘23
Elementary Renovations – Summer of ‘24
Frank White Demolition – May/June of ‘23
Secondary Additions – Commence Summer of ‘23 – Complete August of ’24
Secondary Additions (ALC/Trans./Kitchen) – Commence Summer of ‘24 and – Complete
May of ’25 (Reference Phasing Plan)
Secondary Phase 1 Renovations – Summer of ’24 (Reference Phasing Plan)
Secondary Phase 2 Renovations – Summer of ’25 (Reference Phasing Plan)

## Slide 6
Questions?