## Slide 1
Park Rapids Additions and Renovations
PARK RAPIDS PUBLIC SCHOOLS
Board Update
February 7th, 2022

## Slide 2
What’s Been Done?
Park Rapids Additions and Renovations
Navigating through the Schematic Design Phase
Held User Group Meetings 1 through 3
  Met with all staff and administration
  Listened and documented needs and identified required programming
Weekly Design Coordination Meetings
  Coordination meetings with all design disciplines
Surveying has Commenced
  Working to complete a Certificate of Survey
Met with Staff to Kick-off Mechanical/Electrical/Technology design

## Slide 3
What’s Been Done?
Park Rapids Additions and Renovations
Planning Frank White Move-out / 7th and 8th Move / Early Childhood Move
  A sub-committee has been formed to address this
  Hope to vacate Frank White Completely by March/April of ‘23

## Slide 4
Upcoming
Park Rapids Additions and Renovations
Design Development Phase!
  This phase further identifies detail
  We’re getting close to getting to this phase
User Group Meetings #4 and #5 within the Design Development Phase
  These meetings will get into more detail of the spaces
Move Forward with the Tennis Court Design
Continue with Weekly Design Coordination Meetings
Continue Frank White / 7th and 8th Move / Early Childhood Move

## Slide 5
Preliminary Schedule – Subject to Change
Park Rapids Additions and Renovations
Tennis Courts – Summer of ‘22
Bus Garage – Summer of ‘23
Elementary Parent Pick-up / Drop-off – Summer of ‘23
Elementary Renovations – Summer of ‘24
Frank White Relocation – TBD
Frank White Demolition – May/June of ‘23
Secondary Additions – Commence Summer of ‘23 – Complete June of ‘24
Secondary Phase 1 Renovations – Summer of ‘24
Secondary Phase 2 Renovations – Summer of ‘25

## Slide 6
Questions?