## Slide 1
Park Rapids Additions and Renovations
PARK RAPIDS PUBLIC SCHOOLS
Board Update
March 7th, 2023

## Slide 2
What’s Been Done?
Park Rapids Additions and Renovations
Opened bids for the High School Improvements project
  Opened bids successfully!
Opened bids for the Century Site Improvements project
  Also Opened bids successfully!
Opening bids on Tuesday for the Bus Garage
Continue to make progress on the Elementary Renovations project

## Slide 3
What’s Been Done? (continued)
Park Rapids Additions and Renovations
Weekly Design Coordination Meetings
  Coordination meetings with all design disciplines

## Slide 4
Upcoming
Park Rapids Additions and Renovations
Bus Garage Bid Opening
Bus Garage, Bid Opening
Continue Design Development Documents at Century Renovations
Planning for Construction!

## Slide 5
Upcoming (cont.)
Park Rapids Additions and Renovations
Current Bid Opening Schedule
  3/7/23 Bus Garage
  12/13/23 Century Renovations (date may change)

## Slide 6
Preliminary Overall Schedule – Subject to Change
Park Rapids Additions and Renovations
Tennis Courts – Summer of ‘22
Bus Garage – Summer of ‘23
Elementary Parent Pick-up / Drop-off – Summer of ‘23
Elementary Renovations – Summer of ‘24
Frank White Demolition – May/June of ‘23
Secondary Additions – Commence Summer of ‘23 – Complete August of ’24
Secondary Additions (ALC/Trans./Kitchen) – Commence Summer of ‘24 and – Complete
May of ’25 (Reference Phasing Plan)
Secondary Phase 1 Renovations – Summer of ’24 (Reference Phasing Plan)
Secondary Phase 2 Renovations – Summer of ’25 (Reference Phasing Plan)

## Slide 7
Questions?