## Slide 1
Park Rapids Additions and Renovations
PARK RAPIDS PUBLIC SCHOOLS
Board Update
April 4th, 2022

## Slide 2
What’s Been Done?
Park Rapids Additions and Renovations
Completed Schematic Design at the Elementary and Secondary
Held User Group Meetings 1 through 4
  Moved into the next step of design and continue to share the plan, gain
  input and communicate with staff and administration
Weekly Design Coordination Meetings
  Coordination meetings with all design disciplines
Planning/Coordinating the Frank White Move-out / 7th and 8th Move / Early Childhood Move
  A sub-committee has been formed to address this
  Hope to vacate Frank White Completely by March/April of ‘23
Scheduled the Soil Investigation Work at Parking Areas and New Construction

## Slide 3
What’s Been Done?
Park Rapids Additions and Renovations
Tennis Courts are Out-to-bid
  Calling potential contractors gain interest
  Answering potential contractor questions

## Slide 4
Upcoming
Park Rapids Additions and Renovations
Design Development Phase!
  Continue to make progress in this design phase
User Group Meeting #5 within the Design Development Phase
  These will be more detailed and will include Mechanical, Electrical
  and Technology Discussions
Open Bids for the Tennis Court Project
Commence with Design of the Parking Areas, Playgrounds and Bus Garage
Continue Frank White / 7th and 8th Move / Early Childhood Move

## Slide 5
Preliminary Overall Schedule – Subject to Change
Park Rapids Additions and Renovations
Tennis Courts – Summer of ‘22
Bus Garage – Summer of ‘23
Elementary Parent Pick-up / Drop-off – Summer of ‘23
Elementary Renovations – Summer of ‘24
Frank White Relocation – TBD
Frank White Demolition – May/June of ‘23
Secondary Additions – Commence Summer of ‘23 – Complete June of ‘24
Secondary Phase 1 Renovations – Summer of ‘24
Secondary Phase 2 Renovations – Summer of ‘25

## Slide 6
Questions?