## Slide 1
Park Rapids Additions and Renovations
PARK RAPIDS PUBLIC SCHOOLS
Board Update
May 1st, 2023

## Slide 2
What’s Been Done?
Park Rapids Additions and Renovations
High School Improvements
  Contracts have been issued
  Planning / Scheduling
  Received CUP from the City
  Nearly completed w/ State Plan Review
  State Plumbing Plan Review was Completed
  Commenced Interior Site Selective Demo at Frank White
  Commenced Pre-Installation Meetings
  Preparing for Construction!

## Slide 3
What’s Been Done?
Park Rapids Additions and Renovations
Century Site Improvements
  Contracts have been issued
  Planning / Scheduling
  Received the CUP from the City
  State Plumbing Plan Review Complete
  Playground Equipment Has Been Delivered
  Preparing for Construction!

## Slide 4
What’s Been Done?
Park Rapids Additions and Renovations
Bus Garage
  Contracts have been issued
  Planning / Scheduling
  Received the CUP from the City
  Currently in State Plumbing Plan Review
  Currently in State Building Plan Review
  Metal Building Has Been Ordered
  Preparing for Construction!

## Slide 5
What’s Been Done?
Park Rapids Additions and Renovations
Elementary Renovations
  Currently in the Design Development Phase to be bid in December

## Slide 6
Upcoming
Park Rapids Additions and Renovations
Design Development Documents at Century Renovations
Planning for Construction!

## Slide 7
Overall Schedule
Park Rapids Additions and Renovations
Bus Garage – Summer of ’23 w/ Substantial Completion Early February of ‘24
Elementary Parent Pick-up / Drop-off – Summer of ‘23
Elementary Renovations – Summer of ‘24
Secondary Additions – Commence Summer of ‘23 – Complete August of ’24
Secondary Additions (ALC/Trans./Kitchen) – Commence Summer of ‘24 and – Complete
May of ’25 (Reference Phasing Plan)
Secondary Phase 1 Renovations – Summer of ’24 (Reference Phasing Plan)
Secondary Phase 2 Renovations – Summer of ’25 (Reference Phasing Plan)

## Slide 8
Questions?