## Slide 1
Park Rapids Additions and Renovations
PARK RAPIDS PUBLIC SCHOOLS
Board Update
Tennis Court – Recommendation to Award
May 2nd, 2022

## Slide 2
What’s Been Done?
Park Rapids Additions and Renovations
Design Development (DD) Progress, Approximately 50% Complete
Held User Group Meetings 1 through 4
  Moved into the next step of design and continue to share the plan, gain
  input and communicate with staff and administration
Weekly Design Coordination Meetings
  Coordination meetings with all design disciplines
Planning/Coordinating the Frank White Move-out / 7th and 8th Move / Early Childhood Move
  A sub-committee has been formed to address this
  Hope to vacate Frank White Completely by March/April of ‘23
Scheduled the Soil Investigation Work at Parking Areas and New Construction

## Slide 3
What’s Been Done?
Park Rapids Additions and Renovations
Bid out the Tennis Courts
Held a Staff Tour at Sartell Schools

## Slide 4
Upcoming
Park Rapids Additions and Renovations
Design Development Phase!
  Continuing to make progress in this design phase
User Group Meeting #5 within the Design Development Phase
  Scheduled for this week
Award and Start Construction of the New Tennis Courts
Continue with Design of the Parking Areas, Playgrounds and Bus Garage
Continue Frank White / 7th and 8th Move / Early Childhood Move

## Slide 5
Preliminary Overall Schedule – Subject to Change
Park Rapids Additions and Renovations
Tennis Courts – Summer of ‘22
Bus Garage – Summer of ‘23
Elementary Parent Pick-up / Drop-off – Summer of ‘23
Elementary Renovations – Summer of ‘24
Frank White Relocation – TBD
Frank White Demolition – May/June of ‘23
Secondary Additions – Commence Summer of ‘23 – Complete June of ’24
Secondary Additions (ALC/Kitchen) – Commence Summer of ‘24 and – Complete
May of ‘25
Secondary Phase 1 Renovations – Summer of ‘24
Secondary Phase 2 Renovations – Summer of ‘25

## Slide 6
Tennis Courts – Recommendation to Award
Park Rapids Additions and Renovations
Received (4) Proposals – Good Coverage!
Low Contractor, Gladen, Under Estimate
Contractor Intends on Starting Soon

## Slide 7
Park Rapids Additions and Renovations

## Slide 8
Park Rapids Additions and Renovations

## Slide 9
Park Rapids Additions and Renovations

## Slide 10
Tennis Courts – Recommendation to Award
Park Rapids Additions and Renovations
We recommend awarding the contract to Gladen Construction, Inc.

## Slide 11
Questions?