## Slide 1
Park Rapids Additions and Renovations
PARK RAPIDS PUBLIC SCHOOLS
Board Update
June 6th, 2022

## Slide 2
What’s Been Done?
Park Rapids Additions and Renovations
Design Development (DD) Progress, Approximately 75% Complete
Weekly Design Coordination Meetings
  Coordination meetings with all design disciplines
Planning/Coordinating the Frank White Move-out / 7th and 8th Move / Early Childhood Move
  A sub-committee has been formed to address this
  Hope to vacate Frank White Completely by March/April of ‘23
Soil Investigation Work Completed
Commenced with Tennis Court Construction

## Slide 3
Tennis Court Update
Park Rapids Additions and Renovations
Demolition and Existing Subgrade Removal – Complete
Next Steps
  Bring to grade with new fill
  Paving
  Surfacing / Striping
  Fencing / Equipment

## Slide 4
Tennis Court Update – Schedule
Park Rapids Additions and Renovations

## Slide 5
Tennis Court Update

## Slide 6
Tennis Court Update

## Slide 7
Tennis Court Update

## Slide 8
Upcoming
Park Rapids Additions and Renovations
Design Development Phase
  Work towards completing this phase
Continue Construction at the Tennis Court
Continue with Design of the Parking Areas, Playgrounds and Bus Garage
Continue Frank White / 7th and 8th Move / Early Childhood Move Discussions

## Slide 9
Preliminary Overall Schedule – Subject to Change
Park Rapids Additions and Renovations
Tennis Courts – Summer of ‘22
Bus Garage – Summer of ‘23
Elementary Parent Pick-up / Drop-off – Summer of ‘23
Elementary Renovations – Summer of ‘24
Frank White Relocation – TBD
Frank White Demolition – May/June of ‘23
Secondary Additions – Commence Summer of ‘23 – Complete June of ’24
Secondary Additions (ALC/Kitchen) – Commence Summer of ‘24 and – Complete
May of ‘25
Secondary Phase 1 Renovations – Summer of ‘24
Secondary Phase 2 Renovations – Summer of ‘25

## Slide 10
Questions?