## Slide 1
Park Rapids Additions and Renovations
PARK RAPIDS PUBLIC SCHOOLS
Board Update
Metal Panel Refinish – Recommendation to Award
July 11, 2022

## Slide 2
What’s Been Done?
Park Rapids Additions and Renovations
Secondary Design Development (DD) Has Been Completed
  This is a major milestone!
Weekly Design Coordination Meetings
  Coordination meetings with all design disciplines
Construction of the Tennis Courts
Commenced with Playground Discussions / Planning
Received Bids for the Metal Panel Refinish project

## Slide 3
Tennis Court Update
Park Rapids Additions and Renovations
Asphalt has been placed
  All inspections have passed
Next Steps
  Fencing
  Surfacing
  Equipment
  Intend on being complete by the end of the month

## Slide 4
Tennis Court Update

## Slide 5
Tennis Court Update

## Slide 6
Tennis Court Update

## Slide 7
Upcoming
Park Rapids Additions and Renovations
Design Development Phase for Secondary
  Complete the DD Estimate
  Meet on the 14th to discuss the D.D. package
Continue Construction of the Tennis Court
Continue with Design of the Parking Areas, Playgrounds and Bus Garage and Elementary

## Slide 8
Preliminary Overall Schedule – Subject to Change
Park Rapids Additions and Renovations
Tennis Courts – Summer of ‘22
Bus Garage – Summer of ‘23
Elementary Parent Pick-up / Drop-off – Summer of ‘23
Elementary Renovations – Summer of ‘24
Frank White Demolition – May/June of ‘23
Secondary Additions – Commence Summer of ‘23 – Complete June of ’24
Secondary Additions (ALC/Trans./Kitchen) – Commence Summer of ‘24 and – Complete
May of ’25 (Reference Phasing Plan)
Secondary Phase 1 Renovations – Summer of ’24 (Reference Phasing Plan)
Secondary Phase 2 Renovations – Summer of ’25 (Reference Phasing Plan)

## Slide 9
Metal Panel Refinish – Recommendation to Award
Park Rapids Additions and Renovations
June 9th, an RFP was issued to Refinish the existing metal panels
  Includes sandblasting to prepare metal panels for new finish
  Refinishing with a High Performance Coating
    Epoxy Base Coat
    Acrylic Polyurethane Top Coat
(3) Bids Received:
  Gen4 Sandblast and Paint - $122,850.00
  Merit Painting, Inc. - $126,000.00
  Eco Sandblast and Paint - $174,500.00

## Slide 10
Metal Panel Refinish – Recommendation to Award
Park Rapids Additions and Renovations
We recommend awarding the contract to Gen4 Sandblast and Paint

## Slide 11
Metal Panel Refinish Areas
Park Rapids Additions and Renovations

## Slide 12
Questions?