## Slide 1
Park Rapids Additions and Renovations
PARK RAPIDS PUBLIC SCHOOLS
Secondary Design Development
July 25, 2022

## Slide 2
Secondary Design Development
Park Rapids Additions and Renovations
We’ll Review the Following:
  Plan Review
  High School Phasing / Schedule
  Construction Estimate

## Slide 3
Secondary Design Development – Plan Review
Park Rapids Additions and Renovations

## Slide 4
Secondary Design Development – Plan Review
Park Rapids Additions and Renovations

## Slide 5
Secondary Design Development – Plan Review
Park Rapids Additions and Renovations

## Slide 6
Secondary Design Development – Plan Review
Park Rapids Additions and Renovations
JLG Presentation

## Slide 7
Phase 1 Additions June ‘23 to August ‘24

## Slide 8
Phase 1 Renovations / Phase 2 Additions Major Renovation – June ‘24 thru August ‘24
Kitchen/ALC/Transportation Additions – June ‘24 through March ‘25

## Slide 9
Phase 2 Renovations High School Classrooms - Sept ‘24 through March ‘25

## Slide 10
Phase 3 Renovations Locker Rooms, Concessions and CTE – Summer of ‘25

## Slide 11
Secondary Design Development - Schedule
Park Rapids Additions and Renovations
Task Name | Duration | Start | Finish
Secondary Additions and Renovations - Precon Schedule | 390 days | Tue 11/2/21 | Mon 5/1/23
Preconstruction | 16 days | Tue 11/2/21 | Tue 11/23/21
Schematic Design | 100 days | Tue 11/2/21 | Mon 3/21/22
Design Development | 85 days | Tue 3/22/22 | Mon 7/18/22
Construction Documents | 210 days | Tue 7/12/22 | Mon 5/1/23
Precast Bid Package #1 Complete by Design Team | 0 days | Fri 8/19/22 | Fri 8/19/22
Construction Documents Process | 105 days | Tue 7/12/22 | Mon 12/5/22
ICS Budget / Schedule Preparation | 10 days | Tue 12/6/22 | Mon 12/19/22
CD Board Approval | 0 days | Mon 12/19/22 | Mon 12/19/22
Bid Procurement | 26 days | Tue 12/20/22 | Tue 1/24/23
Bid Opening | 0 days | Tue 1/24/23 | Tue 1/24/23
Critical Submittals | 20 days | Wed 1/25/23 | Tue 2/21/23
Contract Procurement | 30 days | Wed 1/25/23 | Tue 3/7/23
State Plan Review | 95 days | Tue 12/20/22 | Mon 5/1/23
Task Name | Duration | Start | Finish
Frank White Demolition | 15 days | Mon 5/15/23 | Fri 6/2/23
New Construction - South Additions and HS Admin Additions | 305 days | Mon 6/5/23 | Fri 8/2/24
Phase 1 Renovations - Media and East Clasrooms / Bathrooms | 60 days | Mon 6/3/24 | Fri 8/23/24
New Construction - Kitchen/ALC/Transportation | 195 days | Mon 6/3/24 | Fri 2/28/25
Phase 2 Renovations - West Classrooms (High School) | 135 days | Mon 8/26/24 | Fri 2/28/25
Phase 3 Renovations - Locker Room, Concessions, CTE | 60 days | Mon 6/2/25 | Fri 8/22/25

## Slide 12
Secondary Design Development - Estimate
Park Rapids Additions and Renovations

## Slide 13
Secondary Design Development - Estimate
Park Rapids Additions and Renovations

## Slide 14
Summary

## Slide 15
Secondary Design Development
Park Rapids Additions and Renovations
We Recommend to Approve the Secondary Design Development as Presented
with the Authorization to proceed with Construction Documents

## Slide 16
Questions?