## Slide 1
Park Rapids Additions and Renovations
PARK RAPIDS PUBLIC SCHOOLS
Board Update
High School – BP #1 Precast – Approval to Receive Bids
September 6th, 2022

## Slide 2
What’s Been Done?
Park Rapids Additions and Renovations
Approx. 50% Complete with Construction Documents at Secondary
  Prepared Bid-Pack #1 Precast
Tennis Courts are Substantially Complete
Metal Panel Refinish Project
  Nearing completion
Progress on the Bus Garage Design
  Identified the “Foot Print”
  Have held and will continue to hold, User Group Meetings
Working on Playground Design

## Slide 3
What’s Been Done? (continued)
Park Rapids Additions and Renovations
Weekly Design Coordination Meetings
  Coordination meetings with all design disciplines
Presented to Staff
  Design Status
  Anticipated Schedule

## Slide 4
Tennis Court Pictures

## Slide 5
Tennis Court Pictures

## Slide 6
Tennis Court Pictures

## Slide 7
Tennis Court Pictures

## Slide 8
Upcoming
Park Rapids Additions and Renovations
Continue with Construction Documents at Secondary
  CD Completion (Design), December 5th
Complete the Tennis Court Punchlist
Century Parent Pick-up / Drop-off Design
  Working on DD Estimate
Bus Garage Design
  DD’s Complete, End of October
Playground Design
  Intent is to have installed next summer in conjunction with the Parent Pick-up
  drop-off project

## Slide 9
Preliminary Overall Schedule – Subject to Change
Park Rapids Additions and Renovations
Tennis Courts – Summer of ‘22
Bus Garage – Summer of ‘23
Elementary Parent Pick-up / Drop-off – Summer of ‘23
Elementary Renovations – Summer of ‘24
Frank White Demolition – May/June of ‘23
Secondary Additions – Commence Summer of ‘23 – Complete August of ’24
Secondary Additions (ALC/Trans./Kitchen) – Commence Summer of ‘24 and – Complete
May of ’25 (Reference Phasing Plan)
Secondary Phase 1 Renovations – Summer of ’24 (Reference Phasing Plan)
Secondary Phase 2 Renovations – Summer of ’25 (Reference Phasing Plan)

## Slide 10
Bid Package #1 - Precast
Park Rapids Additions and Renovations
Architectural Precast Wall Panels are scheduled for the Gym
Estimated Valuation, Supply and Install, $810,000
Approximately a 1 yr Lead Time
  To conform to the Construction Schedule, this early Bid Package is necessary
Intending on Opening Bids, September 20th, 2022

## Slide 11
Bid Package #1 - Precast
Park Rapids Additions and Renovations
We recommend approval to procure Architectural Precast bids, Bid Package
#1 – Precast, as presented.

## Slide 12
Questions?